## Feature Roadmap
Phase | Category | Feature | What to Integrate | Priority | Status
Phase 1 | Production Foundation | Real backend integration | Replace mock/client-side simulation with production APIs | Must Have | Not Started
Phase 1 | Production Foundation | Real authentication | JWT/token-based authentication, session persistence, logout and protected requests | Must Have | Not Started
Phase 1 | Production Foundation | Real product catalogue | Load cakes/products/categories from backend instead of mock data | Must Have | Not Started
Phase 1 | Production Foundation | Real cart | Sync cart with backend and keep quantities/prices consistent | Must Have | Not Started
Phase 1 | Production Foundation | Real order creation | Create and persist orders through backend | Must Have | Not Started
Phase 1 | Production Foundation | Address management | Add/edit/delete/select saved delivery addresses with validation | Must Have | Not Started
Phase 1 | Production Foundation | Loading & error states | Handle API failures, empty states, retries and network errors | Must Have | Not Started
Phase 2 | E-commerce | Coupons & discounts | Coupon validation, expiry, minimum order and discount calculation | High | Not Started
Phase 2 | E-commerce | Wishlist / Favorites | Persist favorite cakes/products and show a wishlist screen | High | Not Started
Phase 2 | E-commerce | Reviews & ratings | Allow customers to rate delivered orders and write reviews/photos | High | Not Started
Phase 2 | E-commerce | Reorder | Add items from a previous order directly back to cart | Medium | Not Started
Phase 2 | E-commerce | Scheduled delivery | Select delivery date and available time slot | High | Not Started
Phase 2 | E-commerce | Push notifications | Order confirmation, preparation, out-for-delivery and delivery notifications | High | Not Started
Phase 2 | E-commerce | Order tracking | Real order status updates, courier information and estimated delivery | High | Not Started
Phase 2 | E-commerce | Map/location tracking | Show delivery location/current delivery progress where supported | Medium | Not Started
Phase 2 | E-commerce | Advanced search & filters | Search suggestions, price/rating/flavor/weight/eggless filters and sorting | Medium | Not Started
Phase 3 | Custom Cake | Custom cake builder | Weight, flavor, shape, egg/eggless, reference image and cake message | High | Not Started
Phase 3 | Custom Cake | Custom cake quote workflow | Submit custom request and receive baker quote/approval status | High | Not Started
Phase 3 | AI Features | AI cake recommendation | Recommend cakes based on occasion, budget, flavor, size and preferences | Portfolio | Not Started
Phase 3 | AI Features | AI custom-cake assistant | Convert natural-language cake requirements into a customized cake request | Portfolio | Not Started
Phase 3 | Personalization | Personalized recommendations | Use customer/order history to suggest relevant cakes | Medium | Not Started
Phase 3 | Engineering | Analytics & event tracking | Track searches, product views, cart actions, orders and feature usage | Medium | Not Started
Phase 3 | Engineering | Caching/offline support | Cache catalogue and useful data for better performance/network resilience | Medium | Not Started
Phase 3 | Engineering | Deep linking | Open specific product/order/tracking screens from notifications or shared links | Medium | Not Started
Fix First | Code Quality | Fix navigation inconsistencies | Resolve Category/Categorys, Address naming and incorrect Blog navigation | Must Fix | Not Started
Fix First | Code Quality | Fix broken notification import | Correct the Notificaton.js naming/import issue | Must Fix | Not Started
Fix First | Code Quality | Fix MenuCard props | Align CategoryListing props with MenuCard and product data fields | Must Fix | Not Started
Fix First | Code Quality | Remove hardcoded API IPs | Use environment/configuration for API base URL | Must Fix | Not Started
Fix First | Code Quality | Remove mock checkout behavior | Replace timeout/fake success with real order creation flow | Must Fix | Not Started

## Priority Summary
Priority | Count
Must Have | 7
High | 8
Medium | 7
Portfolio | 2
Must Fix | 5
Note | Payment system intentionally excluded as requested.