## Lists
Status | Weight | Priority | Release
Not Started | 0 | Critical | Launch Critical
In Progress | 0.5 | High | MVP
Blocked | 0 | Medium | Post-MVP
Needs Verification | 0.75 | Low | Future
Done | 1
N/A | 1

## Master Tracker
Task ID | Module ID | Module | Tier | Workstream | Task | Minute Task / Acceptance Detail | Release | Status | Priority | Owner | Dependency / Blocker | Target Date | Notes / Evidence | Source
T0001 | M01 | Identity & Authentication | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0002 | M01 | Identity & Authentication | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0003 | M01 | Identity & Authentication | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0004 | M01 | Identity & Authentication | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0005 | M01 | Identity & Authentication | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0006 | M01 | Identity & Authentication | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0007 | M01 | Identity & Authentication | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0008 | M01 | Identity & Authentication | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0009 | M01 | Identity & Authentication | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0010 | M01 | Identity & Authentication | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0011 | M01 | Identity & Authentication | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0012 | M01 | Identity & Authentication | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0013 | M01 | Identity & Authentication | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0014 | M01 | Identity & Authentication | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0015 | M01 | Identity & Authentication | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0016 | M01 | Identity & Authentication | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0017 | M01 | Identity & Authentication | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0018 | M01 | Identity & Authentication | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0019 | M01 | Identity & Authentication | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0020 | M01 | Identity & Authentication | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0021 | M01 | Identity & Authentication | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0022 | M01 | Identity & Authentication | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0023 | M01 | Identity & Authentication | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0024 | M01 | Identity & Authentication | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0025 | M02 | Customer Accounts | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0026 | M02 | Customer Accounts | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0027 | M02 | Customer Accounts | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0028 | M02 | Customer Accounts | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0029 | M02 | Customer Accounts | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0030 | M02 | Customer Accounts | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0031 | M02 | Customer Accounts | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0032 | M02 | Customer Accounts | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0033 | M02 | Customer Accounts | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0034 | M02 | Customer Accounts | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0035 | M02 | Customer Accounts | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0036 | M02 | Customer Accounts | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0037 | M02 | Customer Accounts | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0038 | M02 | Customer Accounts | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0039 | M02 | Customer Accounts | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0040 | M02 | Customer Accounts | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0041 | M02 | Customer Accounts | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0042 | M02 | Customer Accounts | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0043 | M02 | Customer Accounts | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0044 | M02 | Customer Accounts | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0045 | M02 | Customer Accounts | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0046 | M02 | Customer Accounts | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0047 | M02 | Customer Accounts | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0048 | M02 | Customer Accounts | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0049 | M03 | Baker Accounts | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0050 | M03 | Baker Accounts | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0051 | M03 | Baker Accounts | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0052 | M03 | Baker Accounts | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0053 | M03 | Baker Accounts | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0054 | M03 | Baker Accounts | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0055 | M03 | Baker Accounts | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0056 | M03 | Baker Accounts | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0057 | M03 | Baker Accounts | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0058 | M03 | Baker Accounts | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0059 | M03 | Baker Accounts | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0060 | M03 | Baker Accounts | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0061 | M03 | Baker Accounts | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0062 | M03 | Baker Accounts | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0063 | M03 | Baker Accounts | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0064 | M03 | Baker Accounts | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0065 | M03 | Baker Accounts | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0066 | M03 | Baker Accounts | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0067 | M03 | Baker Accounts | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0068 | M03 | Baker Accounts | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0069 | M03 | Baker Accounts | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0070 | M03 | Baker Accounts | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0071 | M03 | Baker Accounts | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0072 | M03 | Baker Accounts | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0073 | M04 | Baker Onboarding | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0074 | M04 | Baker Onboarding | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0075 | M04 | Baker Onboarding | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0076 | M04 | Baker Onboarding | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0077 | M04 | Baker Onboarding | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0078 | M04 | Baker Onboarding | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0079 | M04 | Baker Onboarding | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0080 | M04 | Baker Onboarding | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0081 | M04 | Baker Onboarding | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0082 | M04 | Baker Onboarding | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0083 | M04 | Baker Onboarding | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0084 | M04 | Baker Onboarding | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0085 | M04 | Baker Onboarding | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0086 | M04 | Baker Onboarding | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0087 | M04 | Baker Onboarding | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0088 | M04 | Baker Onboarding | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0089 | M04 | Baker Onboarding | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0090 | M04 | Baker Onboarding | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0091 | M04 | Baker Onboarding | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0092 | M04 | Baker Onboarding | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0093 | M04 | Baker Onboarding | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0094 | M04 | Baker Onboarding | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0095 | M04 | Baker Onboarding | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0096 | M04 | Baker Onboarding | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0097 | M05 | Verification & Compliance | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0098 | M05 | Verification & Compliance | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0099 | M05 | Verification & Compliance | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0100 | M05 | Verification & Compliance | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0101 | M05 | Verification & Compliance | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0102 | M05 | Verification & Compliance | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0103 | M05 | Verification & Compliance | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0104 | M05 | Verification & Compliance | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0105 | M05 | Verification & Compliance | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0106 | M05 | Verification & Compliance | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0107 | M05 | Verification & Compliance | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0108 | M05 | Verification & Compliance | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0109 | M05 | Verification & Compliance | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0110 | M05 | Verification & Compliance | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0111 | M05 | Verification & Compliance | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0112 | M05 | Verification & Compliance | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0113 | M05 | Verification & Compliance | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0114 | M05 | Verification & Compliance | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0115 | M05 | Verification & Compliance | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0116 | M05 | Verification & Compliance | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0117 | M05 | Verification & Compliance | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0118 | M05 | Verification & Compliance | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0119 | M05 | Verification & Compliance | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0120 | M05 | Verification & Compliance | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0121 | M06 | Marketplace Taxonomy | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0122 | M06 | Marketplace Taxonomy | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0123 | M06 | Marketplace Taxonomy | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0124 | M06 | Marketplace Taxonomy | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0125 | M06 | Marketplace Taxonomy | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0126 | M06 | Marketplace Taxonomy | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0127 | M06 | Marketplace Taxonomy | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0128 | M06 | Marketplace Taxonomy | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0129 | M06 | Marketplace Taxonomy | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0130 | M06 | Marketplace Taxonomy | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0131 | M06 | Marketplace Taxonomy | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0132 | M06 | Marketplace Taxonomy | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0133 | M06 | Marketplace Taxonomy | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0134 | M06 | Marketplace Taxonomy | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0135 | M06 | Marketplace Taxonomy | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0136 | M06 | Marketplace Taxonomy | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0137 | M06 | Marketplace Taxonomy | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0138 | M06 | Marketplace Taxonomy | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0139 | M06 | Marketplace Taxonomy | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0140 | M06 | Marketplace Taxonomy | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0141 | M06 | Marketplace Taxonomy | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0142 | M06 | Marketplace Taxonomy | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0143 | M06 | Marketplace Taxonomy | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0144 | M06 | Marketplace Taxonomy | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0145 | M07 | Storefront | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0146 | M07 | Storefront | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0147 | M07 | Storefront | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0148 | M07 | Storefront | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0149 | M07 | Storefront | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0150 | M07 | Storefront | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0151 | M07 | Storefront | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0152 | M07 | Storefront | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0153 | M07 | Storefront | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0154 | M07 | Storefront | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0155 | M07 | Storefront | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0156 | M07 | Storefront | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0157 | M07 | Storefront | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0158 | M07 | Storefront | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0159 | M07 | Storefront | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0160 | M07 | Storefront | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0161 | M07 | Storefront | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0162 | M07 | Storefront | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0163 | M07 | Storefront | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0164 | M07 | Storefront | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0165 | M07 | Storefront | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0166 | M07 | Storefront | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0167 | M07 | Storefront | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0168 | M07 | Storefront | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0169 | M08 | Catalogue | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0170 | M08 | Catalogue | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0171 | M08 | Catalogue | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0172 | M08 | Catalogue | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0173 | M08 | Catalogue | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0174 | M08 | Catalogue | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0175 | M08 | Catalogue | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0176 | M08 | Catalogue | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0177 | M08 | Catalogue | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0178 | M08 | Catalogue | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0179 | M08 | Catalogue | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0180 | M08 | Catalogue | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0181 | M08 | Catalogue | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0182 | M08 | Catalogue | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0183 | M08 | Catalogue | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0184 | M08 | Catalogue | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0185 | M08 | Catalogue | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0186 | M08 | Catalogue | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0187 | M08 | Catalogue | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0188 | M08 | Catalogue | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0189 | M08 | Catalogue | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0190 | M08 | Catalogue | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0191 | M08 | Catalogue | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0192 | M08 | Catalogue | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0193 | M09 | Product Configuration | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0194 | M09 | Product Configuration | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0195 | M09 | Product Configuration | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0196 | M09 | Product Configuration | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0197 | M09 | Product Configuration | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0198 | M09 | Product Configuration | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0199 | M09 | Product Configuration | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0200 | M09 | Product Configuration | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0201 | M09 | Product Configuration | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0202 | M09 | Product Configuration | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0203 | M09 | Product Configuration | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0204 | M09 | Product Configuration | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0205 | M09 | Product Configuration | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0206 | M09 | Product Configuration | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0207 | M09 | Product Configuration | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0208 | M09 | Product Configuration | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0209 | M09 | Product Configuration | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0210 | M09 | Product Configuration | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0211 | M09 | Product Configuration | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0212 | M09 | Product Configuration | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0213 | M09 | Product Configuration | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0214 | M09 | Product Configuration | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0215 | M09 | Product Configuration | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0216 | M09 | Product Configuration | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0217 | M10 | Standard Orders | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0218 | M10 | Standard Orders | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0219 | M10 | Standard Orders | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0220 | M10 | Standard Orders | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0221 | M10 | Standard Orders | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0222 | M10 | Standard Orders | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0223 | M10 | Standard Orders | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0224 | M10 | Standard Orders | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0225 | M10 | Standard Orders | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0226 | M10 | Standard Orders | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0227 | M10 | Standard Orders | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0228 | M10 | Standard Orders | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0229 | M10 | Standard Orders | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0230 | M10 | Standard Orders | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0231 | M10 | Standard Orders | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0232 | M10 | Standard Orders | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0233 | M10 | Standard Orders | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0234 | M10 | Standard Orders | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0235 | M10 | Standard Orders | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0236 | M10 | Standard Orders | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0237 | M10 | Standard Orders | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0238 | M10 | Standard Orders | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0239 | M10 | Standard Orders | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0240 | M10 | Standard Orders | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0241 | M11 | Custom Orders | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0242 | M11 | Custom Orders | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0243 | M11 | Custom Orders | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0244 | M11 | Custom Orders | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0245 | M11 | Custom Orders | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0246 | M11 | Custom Orders | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0247 | M11 | Custom Orders | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0248 | M11 | Custom Orders | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0249 | M11 | Custom Orders | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0250 | M11 | Custom Orders | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0251 | M11 | Custom Orders | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0252 | M11 | Custom Orders | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0253 | M11 | Custom Orders | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0254 | M11 | Custom Orders | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0255 | M11 | Custom Orders | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0256 | M11 | Custom Orders | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0257 | M11 | Custom Orders | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0258 | M11 | Custom Orders | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0259 | M11 | Custom Orders | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0260 | M11 | Custom Orders | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0261 | M11 | Custom Orders | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0262 | M11 | Custom Orders | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0263 | M11 | Custom Orders | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0264 | M11 | Custom Orders | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0265 | M12 | Quotes & Design Approval | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0266 | M12 | Quotes & Design Approval | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0267 | M12 | Quotes & Design Approval | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0268 | M12 | Quotes & Design Approval | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0269 | M12 | Quotes & Design Approval | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0270 | M12 | Quotes & Design Approval | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0271 | M12 | Quotes & Design Approval | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0272 | M12 | Quotes & Design Approval | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0273 | M12 | Quotes & Design Approval | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0274 | M12 | Quotes & Design Approval | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0275 | M12 | Quotes & Design Approval | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0276 | M12 | Quotes & Design Approval | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0277 | M12 | Quotes & Design Approval | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0278 | M12 | Quotes & Design Approval | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0279 | M12 | Quotes & Design Approval | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0280 | M12 | Quotes & Design Approval | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0281 | M12 | Quotes & Design Approval | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0282 | M12 | Quotes & Design Approval | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0283 | M12 | Quotes & Design Approval | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0284 | M12 | Quotes & Design Approval | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0285 | M12 | Quotes & Design Approval | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0286 | M12 | Quotes & Design Approval | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0287 | M12 | Quotes & Design Approval | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0288 | M12 | Quotes & Design Approval | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0289 | M13 | Conversations | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0290 | M13 | Conversations | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0291 | M13 | Conversations | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0292 | M13 | Conversations | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0293 | M13 | Conversations | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0294 | M13 | Conversations | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0295 | M13 | Conversations | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0296 | M13 | Conversations | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0297 | M13 | Conversations | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0298 | M13 | Conversations | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0299 | M13 | Conversations | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0300 | M13 | Conversations | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0301 | M13 | Conversations | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0302 | M13 | Conversations | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0303 | M13 | Conversations | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0304 | M13 | Conversations | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0305 | M13 | Conversations | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0306 | M13 | Conversations | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0307 | M13 | Conversations | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0308 | M13 | Conversations | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0309 | M13 | Conversations | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0310 | M13 | Conversations | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0311 | M13 | Conversations | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0312 | M13 | Conversations | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0313 | M14 | Direct Payment Records | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0314 | M14 | Direct Payment Records | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0315 | M14 | Direct Payment Records | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0316 | M14 | Direct Payment Records | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0317 | M14 | Direct Payment Records | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0318 | M14 | Direct Payment Records | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0319 | M14 | Direct Payment Records | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0320 | M14 | Direct Payment Records | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0321 | M14 | Direct Payment Records | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0322 | M14 | Direct Payment Records | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0323 | M14 | Direct Payment Records | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0324 | M14 | Direct Payment Records | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0325 | M14 | Direct Payment Records | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0326 | M14 | Direct Payment Records | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0327 | M14 | Direct Payment Records | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0328 | M14 | Direct Payment Records | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0329 | M14 | Direct Payment Records | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0330 | M14 | Direct Payment Records | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0331 | M14 | Direct Payment Records | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0332 | M14 | Direct Payment Records | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0333 | M14 | Direct Payment Records | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0334 | M14 | Direct Payment Records | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0335 | M14 | Direct Payment Records | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0336 | M14 | Direct Payment Records | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0337 | M15 | Fulfilment | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0338 | M15 | Fulfilment | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0339 | M15 | Fulfilment | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0340 | M15 | Fulfilment | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0341 | M15 | Fulfilment | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0342 | M15 | Fulfilment | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0343 | M15 | Fulfilment | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0344 | M15 | Fulfilment | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0345 | M15 | Fulfilment | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0346 | M15 | Fulfilment | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0347 | M15 | Fulfilment | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0348 | M15 | Fulfilment | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0349 | M15 | Fulfilment | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0350 | M15 | Fulfilment | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0351 | M15 | Fulfilment | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0352 | M15 | Fulfilment | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0353 | M15 | Fulfilment | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0354 | M15 | Fulfilment | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0355 | M15 | Fulfilment | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0356 | M15 | Fulfilment | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0357 | M15 | Fulfilment | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0358 | M15 | Fulfilment | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0359 | M15 | Fulfilment | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0360 | M15 | Fulfilment | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0361 | M16 | Reviews & Reputation | Tier 2 light | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0362 | M16 | Reviews & Reputation | Tier 2 light | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0363 | M16 | Reviews & Reputation | Tier 2 light | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0364 | M16 | Reviews & Reputation | Tier 2 light | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0365 | M16 | Reviews & Reputation | Tier 2 light | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0366 | M16 | Reviews & Reputation | Tier 2 light | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0367 | M16 | Reviews & Reputation | Tier 2 light | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0368 | M16 | Reviews & Reputation | Tier 2 light | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0369 | M16 | Reviews & Reputation | Tier 2 light | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0370 | M16 | Reviews & Reputation | Tier 2 light | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0371 | M16 | Reviews & Reputation | Tier 2 light | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0372 | M16 | Reviews & Reputation | Tier 2 light | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0373 | M16 | Reviews & Reputation | Tier 2 light | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0374 | M16 | Reviews & Reputation | Tier 2 light | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0375 | M16 | Reviews & Reputation | Tier 2 light | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0376 | M16 | Reviews & Reputation | Tier 2 light | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0377 | M16 | Reviews & Reputation | Tier 2 light | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0378 | M16 | Reviews & Reputation | Tier 2 light | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0379 | M16 | Reviews & Reputation | Tier 2 light | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0380 | M16 | Reviews & Reputation | Tier 2 light | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0381 | M16 | Reviews & Reputation | Tier 2 light | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0382 | M16 | Reviews & Reputation | Tier 2 light | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0383 | M16 | Reviews & Reputation | Tier 2 light | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0384 | M16 | Reviews & Reputation | Tier 2 light | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0385 | M17 | Notifications | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0386 | M17 | Notifications | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0387 | M17 | Notifications | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0388 | M17 | Notifications | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0389 | M17 | Notifications | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0390 | M17 | Notifications | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0391 | M17 | Notifications | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0392 | M17 | Notifications | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0393 | M17 | Notifications | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0394 | M17 | Notifications | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0395 | M17 | Notifications | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0396 | M17 | Notifications | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0397 | M17 | Notifications | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0398 | M17 | Notifications | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0399 | M17 | Notifications | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0400 | M17 | Notifications | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0401 | M17 | Notifications | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0402 | M17 | Notifications | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0403 | M17 | Notifications | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0404 | M17 | Notifications | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0405 | M17 | Notifications | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0406 | M17 | Notifications | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0407 | M17 | Notifications | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0408 | M17 | Notifications | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0409 | M18 | Subscriptions & Entitlements | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0410 | M18 | Subscriptions & Entitlements | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0411 | M18 | Subscriptions & Entitlements | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0412 | M18 | Subscriptions & Entitlements | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0413 | M18 | Subscriptions & Entitlements | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0414 | M18 | Subscriptions & Entitlements | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0415 | M18 | Subscriptions & Entitlements | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0416 | M18 | Subscriptions & Entitlements | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0417 | M18 | Subscriptions & Entitlements | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0418 | M18 | Subscriptions & Entitlements | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0419 | M18 | Subscriptions & Entitlements | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0420 | M18 | Subscriptions & Entitlements | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0421 | M18 | Subscriptions & Entitlements | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0422 | M18 | Subscriptions & Entitlements | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0423 | M18 | Subscriptions & Entitlements | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0424 | M18 | Subscriptions & Entitlements | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0425 | M18 | Subscriptions & Entitlements | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0426 | M18 | Subscriptions & Entitlements | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0427 | M18 | Subscriptions & Entitlements | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0428 | M18 | Subscriptions & Entitlements | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0429 | M18 | Subscriptions & Entitlements | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0430 | M18 | Subscriptions & Entitlements | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0431 | M18 | Subscriptions & Entitlements | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0432 | M18 | Subscriptions & Entitlements | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0433 | M19 | Platform Billing | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0434 | M19 | Platform Billing | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0435 | M19 | Platform Billing | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0436 | M19 | Platform Billing | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0437 | M19 | Platform Billing | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0438 | M19 | Platform Billing | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0439 | M19 | Platform Billing | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0440 | M19 | Platform Billing | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0441 | M19 | Platform Billing | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0442 | M19 | Platform Billing | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0443 | M19 | Platform Billing | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0444 | M19 | Platform Billing | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0445 | M19 | Platform Billing | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0446 | M19 | Platform Billing | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0447 | M19 | Platform Billing | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0448 | M19 | Platform Billing | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0449 | M19 | Platform Billing | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0450 | M19 | Platform Billing | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0451 | M19 | Platform Billing | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0452 | M19 | Platform Billing | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0453 | M19 | Platform Billing | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0454 | M19 | Platform Billing | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0455 | M19 | Platform Billing | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0456 | M19 | Platform Billing | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0457 | M20 | Files & Media | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0458 | M20 | Files & Media | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0459 | M20 | Files & Media | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0460 | M20 | Files & Media | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0461 | M20 | Files & Media | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0462 | M20 | Files & Media | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0463 | M20 | Files & Media | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0464 | M20 | Files & Media | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0465 | M20 | Files & Media | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0466 | M20 | Files & Media | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0467 | M20 | Files & Media | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0468 | M20 | Files & Media | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0469 | M20 | Files & Media | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0470 | M20 | Files & Media | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0471 | M20 | Files & Media | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0472 | M20 | Files & Media | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0473 | M20 | Files & Media | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0474 | M20 | Files & Media | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0475 | M20 | Files & Media | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0476 | M20 | Files & Media | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0477 | M20 | Files & Media | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0478 | M20 | Files & Media | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0479 | M20 | Files & Media | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0480 | M20 | Files & Media | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0481 | M21 | Moderation & Disputes | Tier 2 light | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0482 | M21 | Moderation & Disputes | Tier 2 light | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0483 | M21 | Moderation & Disputes | Tier 2 light | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0484 | M21 | Moderation & Disputes | Tier 2 light | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0485 | M21 | Moderation & Disputes | Tier 2 light | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0486 | M21 | Moderation & Disputes | Tier 2 light | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0487 | M21 | Moderation & Disputes | Tier 2 light | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0488 | M21 | Moderation & Disputes | Tier 2 light | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0489 | M21 | Moderation & Disputes | Tier 2 light | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0490 | M21 | Moderation & Disputes | Tier 2 light | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0491 | M21 | Moderation & Disputes | Tier 2 light | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0492 | M21 | Moderation & Disputes | Tier 2 light | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0493 | M21 | Moderation & Disputes | Tier 2 light | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0494 | M21 | Moderation & Disputes | Tier 2 light | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0495 | M21 | Moderation & Disputes | Tier 2 light | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0496 | M21 | Moderation & Disputes | Tier 2 light | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0497 | M21 | Moderation & Disputes | Tier 2 light | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0498 | M21 | Moderation & Disputes | Tier 2 light | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0499 | M21 | Moderation & Disputes | Tier 2 light | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0500 | M21 | Moderation & Disputes | Tier 2 light | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0501 | M21 | Moderation & Disputes | Tier 2 light | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0502 | M21 | Moderation & Disputes | Tier 2 light | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0503 | M21 | Moderation & Disputes | Tier 2 light | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0504 | M21 | Moderation & Disputes | Tier 2 light | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0505 | M22 | Admin Operations | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0506 | M22 | Admin Operations | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0507 | M22 | Admin Operations | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0508 | M22 | Admin Operations | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0509 | M22 | Admin Operations | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0510 | M22 | Admin Operations | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0511 | M22 | Admin Operations | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0512 | M22 | Admin Operations | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0513 | M22 | Admin Operations | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0514 | M22 | Admin Operations | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0515 | M22 | Admin Operations | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0516 | M22 | Admin Operations | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0517 | M22 | Admin Operations | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0518 | M22 | Admin Operations | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0519 | M22 | Admin Operations | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0520 | M22 | Admin Operations | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0521 | M22 | Admin Operations | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0522 | M22 | Admin Operations | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0523 | M22 | Admin Operations | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0524 | M22 | Admin Operations | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0525 | M22 | Admin Operations | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0526 | M22 | Admin Operations | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0527 | M22 | Admin Operations | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0528 | M22 | Admin Operations | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0529 | M23 | Audit & Security | Tier 1 | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0530 | M23 | Audit & Security | Tier 1 | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0531 | M23 | Audit & Security | Tier 1 | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0532 | M23 | Audit & Security | Tier 1 | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0533 | M23 | Audit & Security | Tier 1 | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0534 | M23 | Audit & Security | Tier 1 | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0535 | M23 | Audit & Security | Tier 1 | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0536 | M23 | Audit & Security | Tier 1 | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0537 | M23 | Audit & Security | Tier 1 | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0538 | M23 | Audit & Security | Tier 1 | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0539 | M23 | Audit & Security | Tier 1 | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0540 | M23 | Audit & Security | Tier 1 | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0541 | M23 | Audit & Security | Tier 1 | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0542 | M23 | Audit & Security | Tier 1 | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0543 | M23 | Audit & Security | Tier 1 | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0544 | M23 | Audit & Security | Tier 1 | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0545 | M23 | Audit & Security | Tier 1 | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0546 | M23 | Audit & Security | Tier 1 | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0547 | M23 | Audit & Security | Tier 1 | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0548 | M23 | Audit & Security | Tier 1 | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0549 | M23 | Audit & Security | Tier 1 | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0550 | M23 | Audit & Security | Tier 1 | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0551 | M23 | Audit & Security | Tier 1 | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0552 | M23 | Audit & Security | Tier 1 | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0553 | M24 | Analytics | Tier 2 light | Requirements | Freeze MVP requirements & boundaries | Confirm source-of-truth requirements, actor ownership, exclusions and commercial/trust boundaries. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0554 | M24 | Analytics | Tier 2 light | Architecture | Map domain ownership & dependencies | Confirm upstream/downstream modules, state ownership and cross-domain contracts. | Launch Critical | Done |  |  |  |  | Defined in the Master System & Domain Architecture Blueprint / implementation specifications. | HomeBaker App Master Document / current code-review evidence
T0555 | M24 | Analytics | Tier 2 light | Database | Design/verify schema | Tables, columns, types, defaults, nullable rules and lifecycle fields. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0556 | M24 | Analytics | Tier 2 light | Database | Define primary/foreign keys | PK/FK relationships and referential behaviour. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0557 | M24 | Analytics | Tier 2 light | Database | Define constraints/indexes | Unique/check constraints and indexes required for integrity/performance. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0558 | M24 | Analytics | Tier 2 light | Database | Create migration baseline | Move manually-created schema into a reproducible migration/baseline process. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0559 | M24 | Analytics | Tier 2 light | Database | Create seed/test data | Create realistic non-production data for integration and E2E testing. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0560 | M24 | Analytics | Tier 2 light | Backend | Define service/domain layer | Implement canonical business rules server-side. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0561 | M24 | Analytics | Tier 2 light | API | Define API contract | Endpoints, DTOs, pagination/filtering, response/error contracts. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0562 | M24 | Analytics | Tier 2 light | Security | Implement authorization | Actor/object authorization, permissions and sensitive-data boundaries. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0563 | M24 | Analytics | Tier 2 light | Validation | Implement server validation | Authoritative validation and invalid-transition rejection. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0564 | M24 | Analytics | Tier 2 light | Reliability | Implement idempotency/concurrency | Duplicate action protection, version/conflict handling where relevant. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0565 | M24 | Analytics | Tier 2 light | Frontend | Build Customer surface | Customer-facing screens/states where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0566 | M24 | Analytics | Tier 2 light | Frontend | Build Baker surface | Baker-facing screens/states where applicable; mark N/A if not applicable. | MVP | In Progress |  |  |  |  | Useful Baker App UI foundation exists per code-review evidence; production integration still needs verification. | HomeBaker App Master Document / current code-review evidence
T0567 | M24 | Analytics | Tier 2 light | Frontend | Build Admin surface | Admin/support operational surface where applicable; mark N/A if not applicable. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0568 | M24 | Analytics | Tier 2 light | UX | Loading/empty/error/offline states | Intentional UX states, retries, stale-data and permission-denied handling. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0569 | M24 | Analytics | Tier 2 light | Integration | Wire frontend to canonical API | Remove mock/local-only production paths and connect server truth. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0570 | M24 | Analytics | Tier 2 light | Testing | Unit tests | Business rules, validation and utilities. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0571 | M24 | Analytics | Tier 2 light | Testing | API/integration tests | Persistence, authorization, state transitions and failure paths. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0572 | M24 | Analytics | Tier 2 light | Testing | E2E actor journey | Critical end-to-end journey across applicable actors. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0573 | M24 | Analytics | Tier 2 light | Testing | Edge/failure cases | Duplicate taps, stale state, invalid permissions, failures and recovery. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0574 | M24 | Analytics | Tier 2 light | Observability | Logging/metrics/alerts | Operationally useful logs, errors and key module health signals. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0575 | M24 | Analytics | Tier 2 light | Documentation | Document implementation | API/schema/runbook/decision notes needed to operate and maintain. | MVP | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0576 | M24 | Analytics | Tier 2 light | Release | Production readiness review | Security, data, rollback, monitoring and release-gate review. | Launch Critical | Not Started | [5 empty] | HomeBaker App Master Document / current code-review evidence
T0577 | P00 | Project Foundation |  | Architecture | Freeze modular-monolith + PostgreSQL baseline | Modular monolith first; PostgreSQL operational source of truth. | Launch Critical | Done |  |  |  |  | Defined in master architecture blueprint. | HomeBaker App Master Document
T0578 | P00 | Project Foundation |  | Architecture | Preserve viable existing UI while replacing weak foundations | Do not rewrite useful UI solely to conform to a new architecture. | MVP | Done |  |  |  |  | Defined architecture principle. | HomeBaker App Master Document
T0579 | P00 | Project Foundation |  | Configuration | Remove production hardcoding | Categories, plans, limits, statuses, pricing and configuration must come from DB/API/Admin. | Launch Critical | In Progress |  |  |  |  | Current code review identifies hardcoded configuration requiring productionisation. | HomeBaker App Master Document
T0580 | P00 | Project Foundation |  | Backend | Replace direct client API/business logic shortcuts | Centralize canonical backend business rules and data access. | Launch Critical | In Progress |  |  |  |  | Current code review identifies direct API calls/weak foundations. | HomeBaker App Master Document
T0581 | P00 | Project Foundation |  | Data | Reproduce current PostgreSQL schema via migrations | Capture manually-created database schema in a repeatable migration/baseline workflow. | Launch Critical | Not Started |  |  |  |  | Current development path uses manually-created PostgreSQL schema. | HomeBaker App Master Document
T0582 | P00 | Project Foundation |  | Data | Load realistic test/seed data | All current tables are treated as empty; seed realistic actor/catalogue/order scenarios. | Launch Critical | Not Started |  |  |  |  | Needed before meaningful integration/E2E verification. | HomeBaker App Master Document
T0583 | P01 | Shared Frontend |  | Frontend | Shared design tokens/primitives | Create consistent tokens/primitives across Customer, Baker and Admin surfaces. | MVP | Not Started |  |  |  |  | Specified in shared frontend blueprint. | HomeBaker App Master Document
T0584 | P01 | Shared Frontend |  | Frontend | Separate server/form/UI/device state | Avoid giant client state store; canonical remote records stay server-owned. | Launch Critical | Not Started |  |  |  |  | Specified in shared frontend blueprint. | HomeBaker App Master Document
T0585 | P01 | Shared Frontend |  | Frontend | Typed query keys/cache invalidation | Actor/business-scoped query keys and safe invalidation. | MVP | Not Started |  |  |  |  | Specified in shared frontend blueprint. | HomeBaker App Master Document
T0586 | P01 | Shared Frontend |  | Frontend | Authentication shell & secure token storage | Secure mobile token storage, controlled refresh, cache clearing on logout. | Launch Critical | Not Started |  |  |  |  | Specified in shared frontend blueprint. | HomeBaker App Master Document
T0587 | P02 | Quality & Security |  | Testing | Create acceptance-test pack | Map frozen MVP requirements to acceptance criteria. | Launch Critical | Not Started |  |  |  |  | Required predecessor to launch readiness. | HomeBaker App Master Document
T0588 | P02 | Quality & Security |  | Testing | Create E2E pack | Baker onboarding->verification->listing->order and Customer discovery->order->payment->fulfilment->review. | Launch Critical | Not Started |  |  |  |  | Required launch evidence. | HomeBaker App Master Document
T0589 | P02 | Quality & Security |  | Security | Security/privacy/trust hardening review | Threat controls, sensitive data, privileged actions, privacy and compliance review. | Launch Critical | Not Started |  |  |  |  | Required predecessor to launch readiness. | HomeBaker App Master Document
T0590 | P03 | Infrastructure |  | DevOps | Development environment reproducibility | Document dependencies, environment variables, DB setup and local start procedure. | Launch Critical | Not Started |  |  |  |  | Needed for repeatable development. | HomeBaker App Master Document
T0591 | P03 | Infrastructure |  | DevOps | Staging environment | Production-like environment with safe test integrations. | Launch Critical | Not Started |  |  |  |  | Needed before release candidate. | HomeBaker App Master Document
T0592 | P03 | Infrastructure |  | DevOps | CI/CD pipeline | Build, test, deploy and rollback workflow. | Launch Critical | Not Started |  |  |  |  | Required predecessor to launch readiness. | HomeBaker App Master Document
T0593 | P03 | Infrastructure |  | Observability | Central logging/error monitoring | Application/API/worker errors and operational health. | Launch Critical | Not Started |  |  |  |  | Required production infrastructure. | HomeBaker App Master Document
T0594 | P03 | Infrastructure |  | Backup | Database backup + restore drill | Automated backups plus verified restoration procedure. | Launch Critical | Not Started |  |  |  |  | Required production operations. | HomeBaker App Master Document
T0595 | P04 | Launch |  | Operations | Select bounded launch geography | Launch only where verified Baker density and serviceability are credible. | Launch Critical | Not Started |  |  |  |  | Launch playbook requirement. | HomeBaker App Master Document
T0596 | P04 | Launch |  | Supply | Recruit founding Baker cohort | Representative, communicative Bakers with realistic coverage/catalogue. | Launch Critical | Not Started |  |  |  |  | Launch playbook requirement. | HomeBaker App Master Document
T0597 | P04 | Launch |  | Supply | Complete Baker launch concierge | Onboard, verify, configure storefront/catalogue/UPI and rehearse orders. | Launch Critical | Not Started |  |  |  |  | Launch playbook requirement. | HomeBaker App Master Document
T0598 | P04 | Launch |  | Supply | Seed credible marketplace supply | Category/subcategory/price/use-case/media/serviceability coverage. | Launch Critical | Not Started |  |  |  |  | Launch playbook requirement. | HomeBaker App Master Document
T0599 | P04 | Launch |  | Rollout | Internal alpha | Controlled team/tester use with realistic data. | Launch Critical | Not Started |  |  |  |  | First rollout stage. | HomeBaker App Master Document
T0600 | P04 | Launch |  | Rollout | Closed beta | Invited Customers around founding Baker geography. | Launch Critical | Not Started |  |  |  |  | Second rollout stage. | HomeBaker App Master Document
T0601 | P04 | Launch |  | Rollout | Soft launch | Limited public acquisition with measured exposure. | Launch Critical | Not Started |  |  |  |  | Third rollout stage. | HomeBaker App Master Document
T0602 | P04 | Launch |  | Rollout | Expanded launch gate | Expand only after operational and marketplace-health evidence. | Post-MVP | Not Started |  |  |  |  | Fourth rollout stage. | HomeBaker App Master Document

## Module Summary
Module ID | Module | Tier | Total Tasks | Done | In Progress | Needs Verification | Blocked | Not Started | N/A | Build %
M01 | Identity & Authentication | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M02 | Customer Accounts | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M03 | Baker Accounts | Tier 1 | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
M04 | Baker Onboarding | Tier 1 | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
M05 | Verification & Compliance | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M06 | Marketplace Taxonomy | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M07 | Storefront | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M08 | Catalogue | Tier 1 | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
M09 | Product Configuration | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M10 | Standard Orders | Tier 1 | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
M11 | Custom Orders | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M12 | Quotes & Design Approval | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M13 | Conversations | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M14 | Direct Payment Records | Tier 1 | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
M15 | Fulfilment | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M16 | Reviews & Reputation | Tier 2 light | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M17 | Notifications | Tier 1 | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
M18 | Subscriptions & Entitlements | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M19 | Platform Billing | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M20 | Files & Media | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M21 | Moderation & Disputes | Tier 2 light | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M22 | Admin Operations | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M23 | Audit & Security | Tier 1 | 24 | 2 | 0 | 0 | 0 | 22 | 0 | 8.333%
M24 | Analytics | Tier 2 light | 24 | 2 | 1 | 0 | 0 | 21 | 0 | 10.42%
P00 | Project Foundation |  | 6 | 2 | 2 | 0 | 0 | 2 | 0 | 50%
P01 | Shared Frontend |  | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0%
P02 | Quality & Security |  | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0%
P03 | Infrastructure |  | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0%
P04 | Launch |  | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0%

## Dashboard
HOME BAKERS - MASTER PROJECT CONTROL TRACKER
KPI | Value | Automated Progress | Value
Total Tasks | 602 | Build Completion | 9.053%
Done | 50 | Verified Completion | 8.306%
In Progress | 9 | Launch Readiness | 10.25%
Needs Verification | 0 | Launch-Critical Open | 429
Blocked | 0
Not Started | 543
How to use this tracker
Your minimum input | Change Status. Add Priority/Owner/Target Date only when useful.
Status meanings | Not Started ¦ In Progress ¦ Needs Verification ¦ Blocked ¦ Done ¦ N/A
Important | Percentages are calculated automatically from task status. Existing UI/schema alone does not equal production-ready.

## Completeness Matrix
Module ID | Module | Requirements | Architecture | Database | Backend | API | Security | Validation | Frontend | Integration | Testing | Observability | Documentation | Release
M01 | Identity & Authentication | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M02 | Customer Accounts | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M03 | Baker Accounts | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M04 | Baker Onboarding | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M05 | Verification & Compliance | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M06 | Marketplace Taxonomy | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M07 | Storefront | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M08 | Catalogue | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M09 | Product Configuration | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M10 | Standard Orders | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M11 | Custom Orders | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M12 | Quotes & Design Approval | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M13 | Conversations | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M14 | Direct Payment Records | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M15 | Fulfilment | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M16 | Reviews & Reputation | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M17 | Notifications | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M18 | Subscriptions & Entitlements | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M19 | Platform Billing | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M20 | Files & Media | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M21 | Moderation & Disputes | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M22 | Admin Operations | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M23 | Audit & Security | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
M24 | Analytics | Done | Done | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started

## Risk Register
Risk ID | Area | Risk | Probability | Impact | Mitigation | Owner | Status | Review Date
R001 | Data | Manual DB creation is not reproducible | High | High | Create migration baseline from current PostgreSQL schema |  | Open
R002 | Integration | Useful UI may still be backed by mock/local-state paths | High | High | Replace with canonical API/server truth and verify end-to-end |  | Open
R003 | Testing | Empty database prevents realistic integration/E2E evidence | High | High | Create controlled seed/test datasets |  | Open
R004 | Scope | Future roadmap items could contaminate MVP | Medium | High | Use Launch Critical/MVP/Post-MVP classification and scope gate |  | Open
R005 | Marketplace | Technical readiness without sufficient Baker supply is not launch readiness | Medium | High | Founding cohort + supply seeding + bounded geography |  | Open

## Decisions & Scope
Decision ID | Area | Question / Change | Type | Impact | Decision | Status | Decision Date | Notes
D001 | Economics | Customer order commission | Frozen Boundary | Critical | Zero commission; Customer pays Baker directly. | Decided
D002 | Architecture | Backend deployment style | Frozen Boundary | High | Modular monolith first. | Decided
D003 | Data | Operational source of truth | Frozen Boundary | High | PostgreSQL. | Decided
D004 | Commerce | Multi-Baker cart | Deferred | High | Not required for MVP. | Deferred
D005 | Payments | Platform custody/escrow for Customer orders | Deferred | Critical | Not part of MVP. | Deferred
D006 | Launch | Verification fee on day one | Open Decision | Medium |  | Open |  | Explicit launch decision required.

## Bugs & Tech Debt
ID | Type | Module | Issue | Severity | Status | Owner | Found Date | Target Fix | Retest | Notes

## Launch Readiness
Gate ID | Area | Launch Gate | Status | Owner | Evidence / Notes
L001 | Scope | MVP scope frozen; no nonessential future work in release candidate | Not Started
L002 | Baker Journey | Onboarding -> verification -> listing -> order operations proven E2E | Not Started
L003 | Customer Journey | Discovery -> standard/custom order -> direct payment record -> fulfilment -> review proven E2E | Not Started
L004 | Monetisation | Free + tiered flat Baker subscription path verified | Not Started
L005 | Security | Security/privacy/trust hardening gates passed | Not Started
L006 | Infrastructure | Production infrastructure, CI/CD, observability, backup and rollback ready | Not Started
L007 | Admin Ops | Verification/support/moderation/billing operational queues rehearsed | Not Started
L008 | Supply | Founding Baker cohort verified and credible catalogue seeded | Not Started
L009 | Geography | Bounded launch geography/serviceability truth configured | Not Started
L010 | Release | Smoke tests, rollback decision rules and launch command ready | Not Started

## Definition of Done
Gate | Requirement | Why it matters
D01 | Requirement/acceptance criteria are frozen and traceable | Prevents ambiguous completion.
D02 | Schema/data changes are reproducible via migration | Prevents environment drift.
D03 | Canonical backend rules implemented | Clients do not become source of truth.
D04 | Authorization and validation implemented | Protects actor/object boundaries.
D05 | Applicable UI connected to canonical API | Mock/local-only success is not production completion.
D06 | Loading/empty/error/permission states handled | Feature works beyond happy path.
D07 | Unit + integration/API tests pass | Core rules and persistence verified.
D08 | Critical E2E journey passes | Cross-layer behaviour proven.
D09 | Logging/operational signals available | Failures can be diagnosed.
D10 | Documentation/runbook updated where needed | Feature can be maintained/operated.
D11 | Release/security checks passed | Feature is production-ready, not merely coded.